## Guidance Sheet
Grant Assurance Data Return template - guidance for LAs
Which projects should I enter Information about?
This template is designed to support LAs to provide details of the projects being funded as a result of their High Needs Provision Capital Allocations (HNPCA). As we have now announced four years of HNPCA funding, LAs should endeavour to include all projects that have used HNPCA funding since 2021-22 up to 2024-25.
LAs should return their updated templates to the department by 1 October 2024 by emailing the completed template to: capital.allocations@education.gov.uk.
LAs should enter data on any known projects that will benefit from investment as a result of the their HNPCA grants. We recognise that at this stage projects may be at different stages in their delivery cycle, and may still be in the process of being fully developed (feasibility, planning, procurement etc). Recording a project on this form does not signal or create a final commitment to this project. LAs are simply requested to provide as complete a picture of intended works as possible. We recognise that not all HNPCA funding may be committed by the 1 October 2024, and therefore the template includes a record of funding that is not currently committed to a project. We would however encourage all LAs to complete the data return template to the best of their ability as this provides valuable data to the department as to the needs and the priorities of the sector in respect of High Needs capital funding, which will help inform future policy development.
If certain information might be considered locally or commercially sensitive (i.e. detailed costings for projects still in procurement or naming specific institutions where this might pre-empt local consultation), LAs should consider whether they can instead provide indicative figures or generic information (e.g. a plan to create a new SEN unit in an unidentified local secondary, pending conclusion of local consultation etc.). If LAs have any queries or concerns about the information requested, they can contact the department at capital.allocations@education.gov.uk for further information or guidance.
How to Enter Information
You can select your LA name from the drop down list in Cell D7. This will auto-populate the LA Number and HNPCA funding in the boxes below. If for any reason there is any discrepancy between this figure and the figure available on the allocations spreadsheet on GOV.UK, the published allocations spreadsheet is final.
Enter the date of completion in Cell L7.
The total amount of funding from HNPCA that your LA has committed and uncommited will auto-complete in cells M12 to M13 as you complete columns O, P, Q and R.
Please complete all yellow boxes, the template will not populate with last year's return.
The blue boxes will auto-populate information. However, if you do need to override these, please email capital.allocations@education.gov.uk and we can provide the password to unprotect the sheet.
Information on individual projects
In the section of the form indicated as Project Information please provide the requested details for each column for any projects being funded as a result of any HNPCA funding. This should include any projects funded as a result of funding allocated through the Safety Valve programme.
When you click on a yellow cell to enter data, instructions of how to enter the data will appear in a yellow box. Cells with a red tab in the corner offer more information and guidance when you hover over these cells.
Some of these fields are protected to only allow specific answers. Please select the most relevant answer from the selection available. Please do not override and provide a different answer as this may not be counted as it is more difficult to process.
Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. When entering cost information please provide details of any proposed costs being met from:
a) your LA's 2021-22 HNPCA grant;
b) your LA's 2022-23 HNPCA grant;
c) your LA's 2023-24 HNPCA grant;
d) your LA's 2024-25 HNPCA grant;
e) housing developer contributions (e.g. s106, CIL); and
f) any additional proposed funding from other sources being used to support the project (e.g. from Basic Need funding, council reserves, borrowing etc.).
If the project will not be using funding from one of the above sources, please put a '0' in the relevant column.
When entering the number of places being delivered by the project, please break these down into:
a) the initial number of new High Needs places expected to be delivered by the project when it is first completed (i.e. places that didn't previously exist or were not suitable for High Needs provision);
b) the total number of new places expected to be delivered by this project once it is at full capacity; and
c) the number of places expected to be reprovided by this project. By 'reprovided places' we mean High Needs places that may have already existed, but were not suited to meet local needs (i.e. places that have been adapted, remodelled or otherwise improved to change their use, bring them up to modern standards or to meet a wider range of need).
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Data validation is drawn from tables on a hidden tables tab. Please do not change the tables or your data will not be consistent and we won't be able to analyse it.
Acronyms used in this return template
AP - Alternative Provision
AY - Academic Year
HN - High Needs
HNPCA - High Needs Provision Capital Allocations
LA - Local Authority
N/A - Not Applicable
PRU - Pupil Referral Unit
RP - Resourced Provision
SEN - Special Educational Needs
SPI - Special Post-16 Institution
TBC - To Be Confirmed
UTC - University Technical College

## Data Return
High Needs Provision Capital Allocations - Assurance Data Return
LAs should return this completed template to the department by 1 October 2024 by emailing the completed template to: capital.allocations@education.gov.uk. For more information on how to complete this form, please see the included Guidance Sheet.
| LOCAL AUTHORITY | Lincolnshire | [7 empty] | Date Template Completed | 2024-09-10
| LA Number | 925
| 2021-22 HNPCA Grant | 2986063.27
| 2022-23 HNPCA Grant | 12901062.56 | [7 empty] | HNPCA total funding
| 2023-24 HNPCA Grant | 12370059.38 | [7 empty] | Total funding committed | 31691806.85
| 2024-25 HNPCA Grant | 3434621.64 | [7 empty] | Total uncommitted funding | 0
Project Information
[7 empty] | Places |  |  | Types of Need |  |  | Indicative/Provisional Funding | [7 empty] | Local Consultation |  | Project delivery
Name of School or Institution | URN (If known) | School or Institution Address | Institution Type | If institution type is 'other', please provide a brief description | Ofsted Judgement | Age Range | Initial number of new HN places operational upon completion | Total number of new HN places the project will deliver once at capacity | Number of reprovided HN places | What is the primary type of need this project will address? | In addition to the primary type of need, will the project address any other types of need? | What is the main purpose of the project? (please provide additional project description in column X) | How much 2021-22 HNPCA funding will the project use? | How much 2022-23 HNPCA funding will the project use? | How much 2023-24 HNPCA funding will the project use? | How much 2024-25 HNPCA funding will the project use? | In addition to core HNPCA, how much Safety Valve funding will the project use? (This only applies to some LAs) | In addition to HNPCA, how much additional funding from housing developer contributions (s106 and CIL) will the project use? | If the project will use any other additional funding, how much funding will this be? | What is the source of this additional funding? | Have you consulted locally regarding this project? | Please give more details about what you have done as part of the consultation process | Has this project been completed? | If the project plans have slipped, why is this? | Which academic year do you anticipate the project being completed and the places being in use? | If the project is no longer going ahead, why is this? | Brief Description of Project Please briefly set out any further details of the project
Lincoln St Christophers School | 120754 | Hykeham Rd, Lincoln, LN6 8AR | Maintained Special school |  | Good | Primary, secondary and post-16 | 47 | 103 | 200 | Other (please provide details in project description) | Yes - The project will address a range of other needs | Other (please provide details in project description) | 859179 | 3560192 | 0 | 0 | 0 | 0 | 24130704 | Basic Need Funding, Condition Funding, Section 77 Receipts, DSG Grant, Council's own funds, Covid Support Fund, Prior Years High Needs Grants (20/21 and earlier). | Consultation completed | Extensive strategic consultation completed in 2018. Local pre-planning planning consultation held in Feb 2021, with extensive key stakeholder involvement. | Yes, the project has been completed | N/A | AY 2024/25 | N/A | New build primary school on separate site and new block and remodel of existing site to become secondary site. Expansion and change to type of need met. Will meet All Needs excluding Primary Need SEMH.
Horncastle St Lawrence School | 142380 | Bowl Alley Lane, Horncastle, LN9 5EJ | Academy/free school - Special |  | Good | Primary and secondary | 98 | 114 | 80 | Other (please provide details in project description) | Yes - The project will address a range of other needs | New facility within an existing provision | 2126884.27 | 4506023.11 | 0 | 0 | 0 | 0 | 8961092.49 | Basic Need Funding, Condition Funding, DSG Grant, Prior Years High Needs Grants (20/21 and earlier). | Consultation completed | Extensive strategic consultation completed in 2018. Local pre-planning planning consultation completed Jan 2022 with extensive key stakeholder involvement. | Yes, the project has been completed | N/A | AY 2023/24 | N/A | New build scheme on existing site commenced September 2022. Expansion and change to type of need met. Will meet All Needs excluding Primary Need SEMH.
Grantham Additional Needs Fellowship | 141254 | Sandon Close, Sandon Rd, Grantham, NG31 9AX | Academy/free school - Special |  | Outstanding | Primary, secondary and post-16 | 77 | 77 | 152 | Other (please provide details in project description) | Yes - The project will address a range of other needs | Expansion of existing provision (existing site) | 0 | 93217.63 | 0 | 0 | 0 | 0 | 2237213 | Basic Need Funding | Consultation completed | Extensive strategic consultation completed in 2018. Local pre-planning planning consultation undertaken by Trust as self-delivery scheme. | Yes, the project has been completed | N/A | AY 2023/24 | N/A | Remodel and provision of new hydrotherapy pool. Consrtuction completed September 2023. Chnage to type of needs met. Will meet All Needs excluding Primary Need SEMH. Merge with Ambergate completed 1st January 2024. HN Placement numbers related to whole school when mergered, not site specific.
Lincoln St Francis School | 120755 | Wickenby Cres, Lincoln, LN1 3TJ | Maintained Special school |  | Outstanding | Primary, secondary and post-16 | 0 | 0 | 166 | Other (please provide details in project description) | Yes - The project will address a range of other needs | Adapting existing provision to meet different needs | 0 | 898925.77 | 0 | 0 | 0 | 0 | 3568074.23 | Basic Need Funding, Condition Funding, Prior Years High Needs Grants (20/21 and earlier). | Consultation completed | Extensive strategic consultation completed in 2018.. Local pre-planning planning consultation completed May 2023, with extensive stakeholder involvement. | No, but the project is in progress and on track | N/A | AY 2024/25 | N/A | Remodel scheme currently in construction. Increase to type of needs met. Will meet All Needs excluding Primary Need SEMH.
Gosberton House Academy | 143257 | 11 Westhorpe Rd, Gosberton, PE11 4EW | Academy/free school - Special |  | Outstanding | Primary | 0 | 0 | 101 | Other (please provide details in project description) | Yes - The project will address a range of other needs | Adapting existing provision to meet different needs | 0 | 3842704.05 | 1353865.32 | 0 | 0 | 0 | 1689688.27 | Condition Funding, DSG Grant, Council's own funds. | Consultation completed | Extensive strategic consultation completed in 2018. Local pre-planning planning consultation completed October 2023, with extensive key stakeholder involvement. | No, the project is in progress but has slipped against original plans | Costs of the project were higher than anticipated | AY 2024/25 | N/A | Remodel and new block scheme currently in construction. Increase to type of needs met. Will meet All Needs excluding Primary Need SEMH.
Springwell Alternative Academy Lincoln | 147195 | Macaulay Drive, Lincoln, LN2 4EL | AP - Academy or free school |  | Good | Primary and secondary | 24 | 56 |  | Other (please provide details in project description) | No - The project will only address its primary type of need | Expansion of existing provision (existing site) | 0 | 0 | 2880000 | 0 | 0 | 0 | 905800.5 | Academy Trust contribution, Council's own funds, various other service area contributions source not yet defined. | Consultation completed |  | No, but the project is in progress and on track | N/A | AY 2024/25 | N/A | Expansion scheme to incorporate partial LA owned premises adjacents to existing provision.
Willoughby Priory Academy | 147414 | South Road, Bourne, PE10 9JD | Academy/free school - Special |  | Good | Primary, secondary and post-16 | TBC | TBC |  | Other (please provide details in project description) | Yes - The project will address a range of other needs | Expansion of existing provision (existing site) | 0 | 0 | 175000 | 0 | 0 | 0 | 0 |  | TBC |  | No, the project has not yet started | N/A | AY 2025/26 | N/A | Planned expansion scheme to existing All Needs Special School. Repurposing of 3 specialist teaching spaces to generic classrooms.
Aegir - A Specialist Academy | 142136 | Sweyn Lane, Gainsborough, Lincolnshire, DN21 1PB | Academy/free school - Special |  | Good | Secondary and post-16 | TBC | TBC |  | Other (please provide details in project description) | Yes - The project will address a range of other needs | Expansion of existing provision (existing site) | 0 | 0 | 376000 | 0 | 0 | 0 | 0 |  | TBC |  | No, the project has not yet started | N/A | AY 2025/26 | N/A | Planned expansion scheme to existing All Needs Special School. Repurposing of 3 specialist teaching spaces to generic classrooms.
Grantham Additional Needs Fellowship - Ambergate | 141254 | Sandon Close, Sandon Rd, Grantham, NG31 9AX | Academy/free school - Special |  | Outstanding | Primary, secondary and post-16 | TBC | TBC |  | Other (please provide details in project description) | Yes - The project will address a range of other needs | Other (please provide details in project description) | 0 | 0 | 5019815.7 | 0 | 0 | 0 | 0 |  | TBC |  | No, the project has not yet started | N/A | AY 2026/27 | N/A | Planned expansion scheme to existing All Needs Speciali School. Expanding into vacant primary school adjacent to site.
Enhanced Resource Provision - Various schools | Across a rnage of mainstream schools | Across a rnage of mainstream schools |  | Maintained and Academy Mainstream Schools |  | Primary and secondary | 100 | 200 | 0 | Other (please provide details in project description) | Yes - The project will address a range of other needs | Entirely new SEN unit within a school | 0 | 0 | 2565378.36 | 3434621.64 | 0 | 0 | 0 |  | TBC |  | No, the project has not yet started | N/A | AY 2025/26 | N/A | LA proposing to develop Mainstream SEND Units and Mainstream AP provision across up to 23 mainstream settings. SEND Units will be in line with LCC's strategic position of all needs provision. Project is currently in development with Executive approval to proceed due 1/10/24.
If you require additional rows added to the table, select the bottom row of the table, and right click > insert row.
Note on O20: Where final costings are not yet known, you may choose to provide indicative figures in the funding columns. Recording information on this form does not signal or create a final commitment, but we do ask that LAs return the template to the best of their ability.
Note on D21: For new projects, the address of the site may not yet be confirmed. If there is a proposed/likely site address, please use this. If not, this column may be left blank.
Note on K21: Reprovided places refer to existing places that will continue to be delivered and will benefit from the project.
Note on N21: More details/examples: - Entirely new school - Entirely new SEN unit within a school - Expansion of existing provision (e.g. additional places created through a new classroom) - Improvement of an existing provision (e.g. new equipment) - New facility within an existing provision (e.g. sensory room or changing facility) - Adapting existing provision to meet different needs - Accessibility - Other (please provide details in project description)
Note on U21: This does not include housing developer contribitions (which can be added to column T). Additional funding sources may include Basic Need funding, council reserves, borrowing etc.

## Tables (hidden)
|  | 2021-22 ALLOCATION | 2022-23 ALLOCATION | 2023-24 ALLOCATION | 2024-25 ALLOCATION
SELECT INSTITUTION TYPE
- | SELECT LOCAL AUTHORITY |  |  |  |  | Independent school | Ofsted inspection judgment | Age Range
301 | Barking and Dagenham | 2159812.71 | 9181089.37 | 5067365.61 | 1093807.65 | 16-19 Academy/free school | Outstanding | Under 5s
302 | Barnet | 2928936.6 | 10104935 | 6685996.64 | 1675023.9 | Academy/free school - Special | Good | Primary
370 | Barnsley | 1460729.06 | 5714239.13 | 4492168.73 | 1261774.04 | Academy/free school - Mainstream | Requires Improvement | Secondary
800 | Bath and North East Somerset | 726954.52 | 4551454.16 | 6903801.98 | 611083.37 | AP - Academy or free school | Inadequate | Primary and secondary
822 | Bedford Borough | 517417.54 | 3160879.3 | 2985935.56 | 736462.72 | AP - PRU (LA maintained) | This institution is not inspected by Ofsted | Post-16
303 | Bexley | 956587.48 | 4062810.94 | 15138051.54 | 1765862.8 | LA nursery school | This institution is open, but has not yet been inspected by Ofsted | Secondary and post-16
330 | Birmingham | 6500323.78 | 21688399.74 | 17731902.03 | 4940122.7 | Maintained school | This institution is not yet open | Primary, secondary and post-16
889 | Blackburn with Darwen | 500000 | 2342618.75 | 2550921.36 | 719973.39 | Maintained Special school | This institution is still to be determined | Other category in 0-25 age-range (please specify in project description)
890 | Blackpool | 500000 | 1464529.14 | 8174736.8 | 634305.99 | Non-Maintained Special School
350 | Bolton | 1327440.51 | 15364796.24 | 4474654.43 | 1298937.12 | Other nursery or early years provision
839 | Bournemouth, Christchurch and Poole | 2365961.51 | 9213326.35 | 5894586.3 | 1341728.33 | Other school |  | Secondary Type of Need
867 | Bracknell Forest | 500000 | 2725564.43 | 2473486.47 | 4623311.73 | Other sixth-form or FE college |  | No - The project will only address its primary type of need
380 | Bradford | 2144168.48 | 9232723.15 | 8869160.4 | 2433636.15 | Special unit/ RP at academy | Primary Type of Need | Yes - The project will address a range of other needs
304 | Brent | 1923257.38 | 5880805.56 | 6786090.03 | 2130266.31 | Special unit/ RP at free school | Autistic Spectrum Disorder | Yes - Autistic Spectrum Disorder
846 | Brighton and Hove | 1029704.8 | 4706298.11 | 3516201.74 | 849323.16 | Special unit/ RP at LA maintained school | Hearing Impairment | Yes - Hearing Impairment
801 | Bristol, City of | 1840832.33 | 11270922.68 | 6727453.54 | 14470505.23 | Special unit/ RP at other school | Moderate Learning Difficulty | Yes - Moderate Learning Difficulty
305 | Bromley | 2450780.28 | 6651669.96 | 6165963.93 | 1764938.28 | SPI (Special Post-16 Institution) | Multi- Sensory Impairment | Yes - Multi- Sensory Impairment
825 | Buckinghamshire | 3555125.39 | 11121278.56 | 9860063.34 | 2797448.43 | Studio school | Other (please provide details in project description) | Yes - Other (please provide details in project description)
351 | Bury | 4370946.66 | 2931468.09 | 3550642.98 | 1077227.05 | University technical college | Physical Disability | Yes - Physical Disability
381 | Calderdale | 551745.88 | 3422213.36 | 2214505.54 | 607364.65 |  | Profound & Multiple Learning Difficulty | Yes - Profound & Multiple Learning Difficulty
873 | Cambridgeshire | 2709339.06 | 22581378.82 | 9104835.14 | 2352233.2 | Main Purpose of Project | Severe Learning Difficulty | Yes - Severe Learning Difficulty
202 | Camden | 2659040.41 | 8639919.17 | 3243472.99 | 456024.45 | Entirely new free school | Social, Emotional and Mental Health | Yes - Social, Emotional and Mental Health
823 | Central Bedfordshire | 1940603.89 | 8760302.88 | 6687071.18 | 1701826.9 | Entirely new LA presumption route school | Specific Learning Difficulty | Yes - Specific Learning Difficulty
895 | Cheshire East | 1263815.33 | 7214677.56 | 5744443.81 | 18251968.28 | Entirely new SEN unit within a school | Speech, Language and Communication | Yes - Speech, Language and Communication
896 | Cheshire West and Chester | 1079140.93 | 5698026.42 | 4700460.85 | 1236794.08 | Expansion of existing provision (existing site) | Visual Impairment | Yes - Visual Impairment
201 | City of London | 0 | 0 | N/A | N/A | Expansion of existing provision (satellite site)
908 | Cornwall | 2442128.57 | 11147439.51 | 9727957.96 | 2804639.5 | Improvement of an existing provision
331 | Coventry | 2426212.34 | 10518024.69 | 6776584.34 | 1686577.16 | New facility within an existing provision
306 | Croydon | 1583319.34 | 5578111.89 | 6043026.32 | 1839744.92 | Adapting existing provision to meet different needs
942 | Cumberland | N/A | N/A | 4387643.04 | 949593.93 | Accessibility | Anticipated completion | Has the project been completed?
909 | Cumbria | 753286.89 | 2672619.17 | N/A | N/A | Other (please provide details in project description) |  | Yes, the project has been completed
841 | Darlington | 500000 | 1736535.73 | 1498065.03 | 463367.27 |  | AY 2021/22 | No, but the project is in progress and on track
831 | Derby | 1565260.46 | 7274447.9 | 5863036.38 | 1640408.57 |  | AY 2022/23 | No, the project is in progress but has slipped against original plans
830 | Derbyshire | 2489980 | 10179536.29 | 13242601.34 | 4204819.41 |  | AY 2023/24 | No, the project has not yet started
878 | Devon | 2145040.68 | 12790568.34 | 12965577.06 | 3772852.11 |  | AY 2024/25 | The project is no longer going ahead
371 | Doncaster | 1064926.66 | 5502839.49 | 5543010.11 | 1614401.75 |  | AY 2025/26
838 | Dorset | 500000 | 4901989.18 | 5743828.05 | 12297935.22 |  | AY 2026/27 | If project has been cancelled
332 | Dudley | 1416043.37 | 6707208.5 | 5877397 | 1718054.1 | Local consultation | AY 2027/28 | N/A
840 | Durham | 2354865.22 | 8510183.33 | 7805806.52 | 2063484.65 | Consultation completed | AY 2028/29 | Funding needed to be prioritised elsewhere
307 | Ealing | 2298819.98 | 6825163.98 | 6754992.16 | 1942886.19 | Consultation in progress | AY 2029/30 | Costs of the project were higher than anticipated
811 | East Riding of Yorkshire | 746801.38 | 4918860.25 | 5156632.27 | 1506106.43 | Consultation planned, but not yet started | Beyond 2030 | Site was not viable
845 | East Sussex | 1273987.46 | 6726770.93 | 6932116.44 | 1935934.37 | TBC | NA | The need for places has changed
308 | Enfield | 1317955.79 | 4485182.52 | 7686580.44 | 2466314.46 | N/A |  | Other
881 | Essex | 5238295.05 | 19345531.04 | 20732949.06 | 5685293.86
390 | Gateshead | 1343333.38 | 3492238.28 | 2063527.53 | 489679.71 |  |  | If the project plans have slipped, why is this?
916 | Gloucestershire | 1988464.83 | 10990306.73 | 8937337.59 | 2280409.91 |  |  | N/A
203 | Greenwich | 2784606.77 | 10020102.81 | 6442424.29 | 1322188.6 |  |  | Funding needed to be prioritised elsewhere
204 | Hackney | 2724671.29 | 10083307.6 | 5105975.4 | 984214.91 |  |  | Costs of the project were higher than anticipated
876 | Halton | 500000 | 2666386.97 | 2198924.32 | 626655.48 |  |  | Site was not viable
205 | Hammersmith and Fulham | 2329829.59 | 4801556.14 | 2242432.59 | 390645.27 |  |  | Difficulties in procuring work/delays in construction
850 | Hampshire | 6789279.35 | 25243509.04 | 24835932.48 | 7621972.65 |  |  | Other
309 | Haringey | 1023937.98 | 9339911.81 | 3364919.1 | 1080832.51
310 | Harrow | 821789.71 | 4138547.45 | 5219519.43 | 1407784.88
805 | Hartlepool | 500000 | 1384647.48 | 975805.18 | 270604.69
311 | Havering | 2206149.31 | 7670580.12 | 5675974.72 | 1289438
884 | Herefordshire | 648121.72 | 2611683.04 | 2819829.82 | 823167.22
919 | Hertfordshire | 4761202.95 | 20007920.5 | 18331544.53 | 4710765.17
312 | Hillingdon | 2872215.63 | 15090653.15 | 6120161.02 | 1505204.77
313 | Hounslow | 2419088.63 | 9508908.73 | 7156678.31 | 1961385.1
921 | Isle of Wight | 500000 | 1050083.77 | 1087841.01 | 356205.65
420 | Isles of Scilly | 500000 | 788074.51 | 211925.49 | 500000
206 | Islington | 1834418.8 | 5638378.53 | 3015407.85 | 559637.22
207 | Kensington and Chelsea | 2383501.3 | 7461394.79 | 3059324.53 | 270788.92
886 | Kent | 6638936.62 | 32108713.21 | 29001569.25 | 7980358.94
810 | Kingston Upon Hull, City of | 1488666.89 | 7192376.88 | 5389726.66 | 1488209.7
314 | Kingston upon Thames | 5114646.33 | 5540177.8 | 3176269.06 | 715027.93
382 | Kirklees | 1609971.75 | 15861570.56 | 6977510.55 | 2040132.19
340 | Knowsley | 509167.24 | 3890300.75 | 2859035.28 | 760081.74
208 | Lambeth | 2541861.32 | 4855965.19 | 3380219.86 | 845627.71
888 | Lancashire | 4724149.55 | 20178483.14 | 19581598.78 | 5559078.56
383 | Leeds | 4574287.88 | 22576594.86 | 11734902.24 | 2321304.59
856 | Leicester | 2013815.67 | 8420348.51 | 5436624.97 | 1290550.8
855 | Leicestershire | 3641554.5 | 12735106.2 | 11759690.01 | 3248168.87
209 | Lewisham | 2550162.94 | 8052934.31 | 5499203.4 | 1337033.13
925 | Lincolnshire | 2986063.27 | 12901062.56 | 12370059.38 | 3434621.64
341 | Liverpool | 3460315.08 | 14301620.34 | 7045886.16 | 1373537.2
821 | Luton | 1243963.04 | 4313023.04 | 3206488.37 | 845667.16
352 | Manchester | 2323799.63 | 12710172.23 | 9429499.48 | 2323156.39
887 | Medway | 1939762.41 | 13540524.23 | 5482269.01 | 1574935.68
315 | Merton | 2192304.74 | 13585092.28 | 4344501.44 | 1233921.71
806 | Middlesbrough | 1159882.3 | 3848136.66 | 2319833.7 | 471911.54
826 | Milton Keynes | 2971552.17 | 10132199.9 | 5546021.24 | 1088334.89
391 | Newcastle upon Tyne | 1461608.45 | 7010093.85 | 4113624.62 | 753678.03
316 | Newham | 2611716.38 | 7296290.68 | 8494621.03 | 2728149.17
926 | Norfolk | 4393596.96 | 14928082.7 | 11853823.34 | 3034143.12
812 | North East Lincolnshire | 883215.54 | 2796066.49 | 1741727.99 | 458089.8
813 | North Lincolnshire | 729278.21 | 3002092.99 | 2992572.67 | 854468
940 | North Northamptonshire | 1296620.5058 | 7137774.67 | 6803123.52 | 1844172.91
802 | North Somerset | 1152776.08 | 3260036.66 | 6919418.33 | 1159472.33
392 | North Tyneside | 663431.61 | 2971475.43 | 6926139.22 | 557991.51
815 | North Yorkshire | 716840.2 | 6543369.57 | 7491930.42 | 2264233.5
929 | Northumberland | 851301.82 | 2665635.95 | 3978192.25 | 1195442.7
892 | Nottingham | 2550244.97 | 11973140.92 | 5985535.04 | 1035259.4
891 | Nottinghamshire | 5316391.06 | 19988078.32 | 16548153.29 | 4629822.83
353 | Oldham | 830008.86 | 3924992.4 | 3396522.64 | 862005.91
931 | Oxfordshire | 3520938.22 | 11987215.81 | 10121255.12 | 2620535.16
874 | Peterborough | 1777784.42 | 7049175.33 | 3777067.11 | 791525.27
879 | Plymouth | 1447787.32 | 6956768.68 | 4505429.14 | 977733.39
851 | Portsmouth | 1181280.62 | 4559375.47 | 2800951.5 | 632119.6
870 | Reading | 954776.21 | 3857086.57 | 3229083.47 | 857535.13
317 | Redbridge | 1847655.81 | 8564467.2 | 5629640 | 1228177.41
807 | Redcar and Cleveland | 807275.48 | 1608840.55 | 1620911.02 | 369088.86
318 | Richmond upon Thames | 6134035.28 | 6926302.6 | 4817630.2 | 1067542.44
354 | Rochdale | 1156818.5 | 5268703.92 | 4943824.78 | 1467113.33
372 | Rotherham | 1059889.81 | 9228873.48 | 3752187.08 | 1002745.16
857 | Rutland | 500000 | 810549.76 | 653392.07 | 172805.84
355 | Salford | 2467910.75 | 10206097.65 | 5055669.69 | 772198.76
333 | Sandwell | 1488855.05 | 6868024.9 | 5753081.72 | 1485421.55
343 | Sefton | 675523.94 | 3737877.68 | 4602768.42 | 1370441.57
373 | Sheffield | 1944425.94 | 10830418.13 | 6805547.35 | 1538633.19
893 | Shropshire | 500000 | 3875585.98 | 4126723.33 | 1141085.94
871 | Slough | 2065765.64 | 5297676.02 | 3850624.22 | 1055806.46
334 | Solihull | 1055762.06 | 4910941.3 | 3826993.47 | 1000250.26
933 | Somerset | 983283.28 | 7683078.75 | 9393696.19 | 2797769.09
803 | South Gloucestershire | 1908231.29 | 8377976.54 | 6249892.6 | 1583333.42
393 | South Tyneside | 632130.41 | 2559951.67 | 1951861.38 | 517220.91
852 | Southampton | 2106601.46 | 7602038.55 | 4424276.2 | 980954.63
882 | Southend-on-Sea | 1061569.94 | 4770879.63 | 2411737.52 | 557610.05
210 | Southwark | 1306335.56 | 9515182.17 | 5957728.84 | 1697691.64
342 | St Helens | 649444.03 | 3242266.7 | 2144123.21 | 525512.49
860 | Staffordshire | 2441299.98 | 10278776.55 | 11760528.56 | 3558948.25
356 | Stockport | 1274115.32 | 5243398.76 | 4656283.24 | 1350642.5
808 | Stockton-on-Tees | 876119.04 | 3458089.77 | 2936671.69 | 736430.18
861 | Stoke-on-Trent | 10199220.46 | 5410992.99 | 5208986.52 | 1491835.7
935 | Suffolk | 2111925.19 | 9381620.67 | 10758718.22 | 3156716.74
394 | Sunderland | 520782.55 | 4280724.63 | 3893510.81 | 1154532.96
936 | Surrey | 6920304.22 | 29572648.76 | 19915638.18 | 5391703.52
319 | Sutton | 1924542.49 | 6430671.29 | 3370191.61 | 824740.11
866 | Swindon | 1598452.1 | 5996536.64 | 3917519.58 | 989736.57
357 | Tameside | 1223336.11 | 5732980.3 | 4865994.02 | 1371829.21
894 | Telford and Wrekin | 1303857.87 | 4401129.98 | 3798337.84 | 1062775.27
883 | Thurrock | 678526 | 4487808.58 | 2994414.65 | 654821.29
880 | Torbay | 530149.55 | 2076643.91 | 2011175.75 | 576354.5
211 | Tower Hamlets | 2638807.37 | 10507823.99 | 5217690.92 | 1053093.72
358 | Trafford | 1676744.46 | 6849264.81 | 4542907.24 | 1213129.43
384 | Wakefield | 1473875.94 | 6076097.78 | 6106417.85 | 1834798.64
335 | Walsall | 1419381.97 | 7227924.29 | 6091965.42 | 1724970.86
320 | Waltham Forest | 1434725.15 | 5514062.59 | 3848027.46 | 1001073.59
212 | Wandsworth | 4837414.07 | 15827055.42 | 6015457.03 | 753530.44
877 | Warrington | 710210.47 | 2727753.24 | 3144056.6 | 1001367.15
937 | Warwickshire | 2747759.95 | 9583082.43 | 7533184.49 | 2027958.72
869 | West Berkshire | 500000 | 2651580.15 | 2298724.34 | 496819.17
941 | West Northamptonshire | 1522119.7242 | 10900195.92 | 8080272.71 | 2132850.49
938 | West Sussex | 4095781.27 | 16479349.06 | 14403828.5 | 3998703.82
943 | Westmorland and Furness | 1040039.03 | 4523712.16 | 2964348.24 | 649082.76
213 | Westminster | N/A | N/A | 4041095.41 | 987532.01
359 | Wigan | 1625569.97 | 5585450.33 | 5162254.91 | 1526636.99
865 | Wiltshire | 2055333.02 | 6753045.92 | 8630681.55 | 2591775.7
868 | Windsor and Maidenhead | 500000 | 2406905.31 | 1870043.63 | 429329.26
344 | Wirral | 1046545.72 | 4390504.05 | 4092751.09 | 1209682
872 | Wokingham | 1266317.22 | 5634050.45 | 9578819.9 | 797168.4
336 | Wolverhampton | 2254086.99 | 5808551.94 | 3876746.81 | 886241.34
885 | Worcestershire | 1539043.81 | 8408559.81 | 8187337.66 | 2394959.65
816 | York | 627439.06 | 7056626.19 | 2270412.45 | 451093.47